## STH Live Project Test Cases
| Project Name | CRC car rental management system
| Team Name | IFB-299 Group 77 (Team-A)
| Documented by | Mingze Dai
| Date of creation | 2018-10-17
| Date of review | 2018-10-25
| User stories involved | User Story 5: Sign up, User Story 24: History Data Mange (Edit), User Story 27: Car description User Story 29: Filtering (Customer accessible page), User Story 30: Filtering (History/Data manage)
Test case ID | Test Objective | Precondition | Steps: | Test data | Expected result / Acceptance criteria | Post-condition | Test Status
CRC_TC_01 | Build up a sign up page so that company users can create their own account to have access to the system | 1. A certain browser should be installed in the user's computer (e.g. Google Chrome) 2. Login page created and have a "sign up" button with hyperlink which connect to the actual sign up page. | 1. Go to the company homepage 2. Cliick on the "sign up" button to create a new account by providing general personal information, such as his first name/last name, address, DOB, phone number, email address, etc Note: If missing an important input field (e.g. password/username) or signing up account already existed, display an error massege. | 1. A valid URL http://127.0.0.1:8000/ 2. user account information 3. connection between webpage and users' database | 1. A highlighted sign up hyperlink below the login button 2. After successgully singup, user information saved into company’s user information database Note: Error message shown up when there’s missing message or account was already existed | Created account can have access to any of the managing page: data managing page/ most popular car details Note: The personal information criteria might vary according to the company’s security level | Passed
CRC_TC_02 | Browse data about the entire history of customer’s personal records and their rental services so that company staff can access and correct the inaccuracies when needed. | 1. The web application is launched on a compatible browser 2. User account is valid 3. Button "edit" and "save" are already created | 1. Log in to the "Management System" menus with currently existing username and password 2. Cliick on the "History" menu to navigate to the History page 3. Click on the "Edit" button to edit existed customers' data 4. Click on the "Save" button to save all changes into users' database | connection between webpage and users' database | 1. Prototype for functionality edit page operates well 2. Pop out a form with input field for company user to insert details when clicking "edit" button 3. Clicking on a button “edit” in the navigation page allows the management staff to edit, add and delete data from the saved data lists 4. Once the “save” button is clicked on, all input user information will be saved into user’s database | Changed data are successfully updated in the database Note: this is a place where company user can manage(edit or delete) the information | Passed
CRC_TC_03 | Browse customer accessible page and provide some general car information based on the company’s database, such as car brand, car body type, and others, so that customers can gain better understandings of company products and services. | 1. Customer has a lunched browser 2. Customer accessible page operates well | 1. Go to the company homepage 2. Click on "if you are a customer" hyperlink | 1.Customer accessiable page 2. connection between rental details and car information | 1. After clicking "if you are a customer", the customer accessiable page pops out 2. All detailed information is shown by clicking a “view more” button next to car information and these details are automatically updated by the car database system. | All information is shown by clicking a “view more” button and these details are automatically updated by the car database system | Passed
CRC_TC_04 | Check the connection between the system and users' database | 1. The web application is launched on a compatible browser 2. Valid account 3. database operates well | 1. Log in to the "Management System" menus with valid username and password 2. Click on the "History" menu to navigate to the customer data page 3. Click on the "edit" and "save"button to edit and save updated customers' detail 4. Fill up the required fields 5. Check if the new information has been uptaded | Login options (username and password) Customer information Car information Order information Reantal store information | All data changed are saved and updated |  | Passed
CRC_TC_05 | Check if the customer accessible page provides a filtering function that sorts cars by different features so that customers can easily search for my ideal car. | 1. Customer has a lunched browser 2. Customer accessible page operates well 3. Sorting function operated well | 1. Open the customer accessible page 2. Click on "Car make name" drop down bar to filtering cap types | Car information | Click on the drop down bar will deplays different kind of car brand | Car information automatically update | Passed
CRC_TC_06 | Check if the history/data manage menu provides a filtering function that sorts data by different dimensions so that company users can efficiently access and manage the data. | 1. The web application is launched on a compatible browser 2. User account is valid 3. Filtering fuction opeartes well | 1. Login to the data manage page 2. Click on the arrowhead at the right of each heading cells | users databse | After clicking the arrowhead, data will sorted by Initial or numerical order unsorted sorted | Order information automatically update | Passed

## Sheet1
| Project Name | Pinland Music School System (PMSS)
| Reference Document | Final_PMSS stories_with_acceptance_criteria_Prioritisation_Estimation.pdf
| Created by | IFB-299 Group 38
| Date of creation | 2018-05-10
| Date of review | 2017-10-09
Test case ID | Test Objective | Precondition | Steps: | Test data | Expected result / Acceptance criteria | Post-condition | Test Status
PMSS_TC_01 | View PMSS welcom page through a URL to perform a general look and see what it offers | 1. The test machine should be configured to run the PMSS project 2. Modern web browsers should be enabled on the test machine | 1. Run the PMSS project on the local instance of the Django server | A valid URL such as http://localhost:8000/ | User should be navigated to the OBAAS welcome page.Welcome page should contain following menu buttons representing different services offered via OBAAS. 1. Create Account 2. Account Balance 3. Service 4. Request 5. Bill Pay 6. Close Account Check the screenshot to get an idea of what screen we are testing | User should be able to navigate to different pages of the OBAAS site using the menu buttons. Note: This info is only additional. Just as a pointer to the tester | Passed
2. Start any web browser of your choice
3. Enter the URL http://127.0.0.1:8000/ in the address bar of the web browser. NOTE: The port number for website URL may vary depending on the server configuration. Please check the server logs to confirm the port number as shown in the following screenshot
OBAAS_TC_02 | User can crete a new account using the OBAAS site | 1. OBAAS site is launched on a compatible browser | 1. Navigate to the account creation page by clicking the "Create Account" button on the menu 2. Fill in all the required field in the account creation form 3. Submit the filled-in form through by clicking the "Submit" button on the form | A valid Username: Josh, Password : 123456, Phone: 0435666067, Address: 1 Queent St, Postcode: 4000 and State: QLD | When the customer clicks the “Create Account” menu item, he or she is navigated to the create account form. Create account page should contain textboxes for Username, Password, Retype Password, Phone Number, Address and Category. All these fields are mandatory, hence customer must provide all these information Check the screenshot to get an idea of what screen we are testing Once the user submits the form with all the mandatory fields filled up, a new account is created with the provided creadential and the account details are stored in the MySQL database. User is presented with a "Success" message in the next page as shown in the following screenshot A randomly generated account number will be allocated to the new user and the relevant details will be stored in the database table | User can use all the available services of the OBAAS site using the newly created account | Passed
OBAAS_TC_03 | Password and Retype password fields in the Account Creation form are masked with asterisk for each character typed in. | 1. OBAAS site is launched on a compatible browser | 1. Navigate to the account creation page by licking the "Create Account" button on the menu 2. Fill in the Password and Confirm Password field in the account creation form | A valid Password: 123456 | The entries in the Password and Confirm Password field should be masked with asteriks as the user types in | User can create an account securely Check the screenshot to get an idea of the expected outcome | Passed
OBAAS_TC_04 | Category textbox in the Account Creation form should be non- editable having a default value of “U”. | 1. OBAAS site is launched on a compatible browser | 1. Navigate to the account creation page by licking the "Create Account" button on the menu | N/A | The "Category" field in the "Create Account" form should be non-editable/diabled with a default valie of "U" as shown in the following figure | Each new user will be created with a default category of "U". The value should be stored in the database table as shown in the following screenshot | Passed
OBAAS_TC_04 | Form contains two buttons, “Submit” button to submit the entered information and “Clear” button to clear the entered information | 1. OBAAS site is launched on a compatible browser | 1. Navigate to the account creation page by clicking the "Create Account" button on the menu 2. Fill in all the required field in the account creation form | A valid Username: Josh, Password : 123456, Phone: 0435666067, Address: 1 Queent St, Postcode: 4000 and State: QLD | Clicking the "Clear" button in the form should clear all the fields in the form while clicking the "Submit" button in the form should submit the form to the backend. | User should be able to clear the entries of all the fields in any form by clicking the "Clear" button. User should be able to submit any form by clicking the "Submit" button | Passed
OBAAS_TC_05 | If the user submits the form without completing all the information, he or she is given a warning message “Please ensure all the fields are completed” in a dialog box which contains an OK button. | 1. OBAAS site is launched on a compatible browser | 1. Navigate to the account creation page by clicking the "Create Account" button on the menu 2. Partially fill in the form | Valid Username: Josh, Password:123456, Account No: 739 | When the user tries to submit a partially filled-in form, a popup message box will appear on the mandatory field asking the user to fill-in the required field Check the screenshot to get an idea of the expected outcome | User needs to fill-in the form completely to successfully submit the form | Passed
OBAAS_TC_06 | If the password doesn’t match with retype password, customer is given a warning message “Entries in the password and retype password do not match. Please ensure password and retype password are the same”. | 1. OBAAS site is launched on a compatible browser | 1. Navigate to the account creation page by clicking the "Create Account" button on the menu 2. Fill in all the required field in the account creation form. | The Password and the Confirm Password field should have different inputs | When the user tries to submit a form where the "Password" and the "Confirm Password" field has different entries an error message will appear on the screen inicating the entries in the two fields do not match Check the screenshot to get an idea of the expected outcome | User needs to correct the error in the password fields in-order to submit the form successfully | Passed
OBAAS_TC_07 | In the login form when the username and password entered by the user do not match with the information stored in the database, he or she is given a warning message “The username/password you entered is incorrect. Please enter correct entries.” | 1. OBAAS site is launched on a compatible browser | 1. Navigate to the account balance page by clicking the "Account Balance" button on the menu 2. Enter invalid Username/Password/ Account Number | Invalid Username, Password and Account Number | When the user enters invalid login details an error message will be displayed to the user saying "Incorrect Login Details. Please enter correct entries" Check the screenshot to get an idea of the expected outcome | User will be re-direccted to the login screen where the user needs to provide correct login details in-order to login successfully | Passed
OBAAS_TC_08 | When a user enters his or her username and password correctly, he or she should be able to log into the system successfully | 1. OBAAS site is launched on a compatible browser 2. An user account is already created on the system | 1. Navigate to the account balance page by clicking the "Account Balance" button on the menu 2. Enter a valid Username/Password/ Account Number | Valid Username: Josh, Password:123456, Account No: 739 | When the user enters correct Username, Password and Account Number, he/she will be logged into the system and their respective account balance will be displayed on the screen Check the screenshot to get an idea of the expected outcome | User can use the available service on the OBAAS site by logging into their personal account | Passed
OBAAS_TC_09 | In the Login form the Password field is masked with asterisk. | 1. OBAAS site is launched on a compatible browser | 1. Navigate to the account balance page by clicking the "Account Balance" button on the menu 2. Enter a valid Username/Password/ Account Number | Valid Username: Josh, Password:123456, Account No: 739 | The entries in the Password field should be masked with asteriks as the user types in Check the screenshot to get an idea of the expected outcome | User can login into their account securely | Passed
OBAAS_TC_10 | User can view their account balance using the "Account Balance" functionality on the site | 1. OBAAS site is launched on a compatible browser 2. An user account is already created on the system | 1. Navigate to the account balance page by clicking the "Account Balance" button on the menu 2. Enter a valid Username/Password/ Account Number | Valid Username: Josh, Password:123456, Account No: 739 | When the customer clicks the “Account Balance” menu item, he or she is navigated to the account balance page. Once the user enters the correct login details, respective account balances are displayed to the user Check the screenshot to get an idea of the expected outcome | User can successfully view their respective account balance | Passed
OBAAS_TC_11 | User can request a cheque book through OBAAS, so that the user can obtain a new cheque book | 1. OBAAS site is launched on a compatible browser 2. An user account is already created on the system | 1. Navigate to the service request page by clicking the "Service Request" button on the menu 2. Enter a valid Username/Password/ Account Number to login | Valid Username: Josh, Password:123456, Account No: 739, Reuest Service: Cheque Book | 1. When the customer clicks the “Service Request” menu item, he or she is navigated to the service request page. Currently, using the Service Request page, the customer can only request a cheque book from the bank 2. Service request page contains a form with text boxes for “Account Number”, “Username” and “Password”. Password field is masked with asterisk. All these fields are mandatory, hence customer must provide all these information 3. If the customer submits having all the information correctly, then he or she is navigated to a page containing a message “New cheque book issued.” Check the screenshot to get an idea of the expected outcome | User can request cheque books through the online service. On receiving a cheque book request, the bank will send a new cheque book, through a courier service, to the customer’s address provided when creating the online account | Passed
OBAAS_TC_12 | The service request form contains a dropdown list having only the "Cheque book" option | 1. OBAAS site is launched on a compatible browser 2. An user account is already created on the system | 1. Navigate to the service request page by clicking the "Service Request" button on the menu 2. Enter a valid Username/Password/ Account Number to login | Valid Username: Josh, Password:123456, Account No: 739, Reuest Service: Cheque Book | Service Request Form contains a dropdown list having only the “Request a cheque book ” option. Check the screenshot to get an idea of the expected outcome | User can request cheque books through the online service. On receiving a cheque book request, the bank will send a new cheque book, through a courier service, to the customer’s address provided when creating the online account | Passed
OBAAS_TC_13 | User can pay bills through OBAAS, so that he/she can perform bill payments online | 1. OBAAS site is launched on a compatible browser 2. An user account is already created on the system 3. Sufficient amount should be available in the user account 4. Biller's account must exist on the site | 1. Navigate to the bill pay page by clicking the "Bill Pay" button on the menu 2. Enter a valid Username/Password/ Account/ Number/ Amount to login 3. Select a biller name from the "Biller" drop-dpwn menu | Valid Username: Josh, Password:123456, Account No: 739 Amount: 200 Biller: Core Energy | 1. “Bill Pay” menu item should be displayed in the welcome page to facilitate bill payments. Currently, using the Bill Pay page, the customer can only pay bills for two different service providers (billers) as shown in the following screenshot 2. When the customer clicks the “Bill Pay” menu item, he or she is navigated to the bill pay page. Bill pay page contains a form with textboxes for “Account Number”, “Username”, “Password” and “Amount”. Password field is masked with asterisk. All these fields are mandatory, hence customer must provide all these information. 3. If the customer submits having all the information correctly, then the entered amount is transferred to the account of the Biller and the same amount is subtracted from the customer’s account. He or she is navigated to a page containing a message “Bill payment successful.” The following screenshot of the database shows that the correct amount was subtracted from the user's account | User can pay bills using the online service. The bill amount will be transferred to the respective biller's account | Passed
OBAAS_TC_14 | If transfer amount is less than the customer’s account balance, then a warning dialog box indicating “Not sufficient funds in the account” is displayed. | 1. OBAAS site is launched on a compatible browser 2. An user account is already created on the system 3. Insufficient amount should be available in the user account 4. Biller's account must exist on the site | 1. Navigate to the bill pay page by clicking the "Bill Pay" button on the menu 2. Enter a valid Username/Password/ Account Number to login 4. Enter an amount greater than the current balance of the user in the Amount field 3. Select a biller name from the "Biller" drop-dpwn menu | Valid Username: Josh, Password:123456, Account No: 739 Amount: 800 Biller: Core Energy NOTE: Try with different amounts to check boundry conditions i.e 400.50/ 500/ 1000/ 99999/ 400.01 | If the transfer amount is less than the customer’s account balance, then a warning dialog box indicating “Not sufficient funds in the account” is displayed. Check the screenshot to get an idea of the expected outcome |  | Passed
OBAAS_TC_15 | User can close their respective account using the online service | 1. OBAAS site is launched on a compatible browser 2. An user account is already created on the system | 1. Navigate to the close account page by clicking the "Close Account" button on the menu 2. Enter a valid Username/Password/ Account Number to login | Valid Username: Josh, Password:123456, Account No: 739 | 1. “Close Account” menu item should be displayed in the welcome page to facilitate closing of accounts 2. When the customer clicks the “Close Account” menu item, he or she is navigated to the close account page. Close account page contains a form with textboxes for “Account Number”, “Username” and “Password”. The following screenshot shown the confirmation page of the "Close Account" page along with the database entry relevant to the user account successfully deleted | User can close their account using the online service. All the relevant account details should be removed from the database. User will not be able to log in with the same credentials