## Burn down chart
Release Burndown
Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 60 | 60
1 |  | 60
2 |  | 40
3 |  | 20
| 0 | 0
Sprint 1 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 31 | 31
19 |  | 31
18 |  | 29
17 |  | 28
16 |  | 25
15 |  | 24
14 |  | 24
13 |  | 24
12 |  | 22
11 |  | 20
10 |  | 19
9 |  | 18
8 |  | 16
7 |  | 15
6 |  | 14
5 |  | 10
4 |  | 8
3 |  | 7
2 |  | 6
1 |  | 6
0 | 0
ALSO DO A SPRINT 2 BURNDOWN AS WELL